## Design Discussions
MileStone - 1 | Scope | WorkBreakdown | Acceptance Criteria | Monitoring | Tech Stack
Create Basic UI , where user can select the total numbers of columns and equation type like unit conversion, calculus, arithmetic etc and can play Nerdle accurately. This will be called App Service | For different types number of columns, type (calculus, arithmetic, conversion etc), few static data will be mainained in a map, and then randomly one of the solved equation ,corresponding to number of columns and type , will be picked, that user need to guess | 1) Application in ReactJS and NodeJS (FrontEnd and Backend) 2) Unit tests 3) Functional Tests 4) Creation of environment (DEV , QA, STAGE, PROD) either using terraform or cloudformations templates 5) Deployment of App service to different environment using Jenkins 6) Collection of metrics on Monitoring services like Prometheus, cloudwatch or New relic 7) Logging integeration with any services like Datadog, splunk or Amazon CloudWatch Logs 8) Alert configuration on collected metrics. 9) Integeration with PagerDuty or or any other incident reporting system *Here Load test is optional, that can be performed, if we now number of requests on an average. This will be useful for caliberation of resourced involved and to get min & max thresholds. | 1) On UI, after selecting the Equation type and Nos. of columns, should create Nos. Of Columns * 6 grid. 2) If user enters wrong equation, then it must show error on UI if equation entered is wrong. 3) If equation entered is correct but NOT the exact equation, then must show, following highlighted information to user a) Total correct characters and at the right place <= GREEN b) Total correct characters but not at the right place <= YELLOW c) Total incorrect characters <= GREY 4) If user guessed correct solution, display success message 5) Logs are getting collected in selected services. 6) Metrics are getting collected. 7) Alert are getting generated 8) Able to deploy successfully using Jenkins on different environment | Metrics to analyse post deployment: 1) Average API calls 2) Average CPU utilization 3) Average Memory utilization 4) Peak load 5) CPU utilization during Peak load 6) Memory utilization during Peak load These metrics will be helpful in scaling application , alert configurations and incident reporting on production | ReactJS NodeJS AWS Services (computing) Jenkins Git Prometheus/CloudWatch/Datadog/New Relic Splunk/AWS Cloudwatch logs PagerDuty
Below are the types of equations that will be handeled, based on static data saved in files corresponding to each type
arithmetic
conversions
calculus
Rather than supporting uploading of config files, we are giving options on UI, to select total number of columns and Equation type,that will be more interactive for user and can provide multiple options to user to guess different sets
MileStone - 2
In milestone 1, we have few sets of solved equations , hardcoaded in backend, and we are picking one of them to be guessed by uesr. So now, we need a Equation Generator Services , that is generating different types of equations (calculus, mathemetic etc ). From here one of the equation is randomly picked , based on columns and equatyion type selected by user. This will be the equation , which user needs to guess on UI. The main aim of this service is to generate equations , based on rules that are applicable to different branches of mathemetics like calculus, algebra, geometry, arithmetic etc Lets call this service Equator Service | Equator Service is internal service that will basically perform 2 different operations. a) It will generate different size (nos. of characters) equations based on different rules applied to different types of equations (like calculus, arithmetic, geometry, algebra etc). It will save the generated equations in the DB b) Whenever any user will load Nerdle , App Service will randomly picy up any equation of Type and Number of column selected by user, and will save in some cache (say Redis ) with some temporary UserId and equation selected from DB. This will reduce DB Request units. c) Whenever user will submit any equation, this service wlll evaluate the correctness of submitted equation , and if correct , will send below data as response: a) Total correct characters and at the right place b) Total correct characters but not at the right place c) Total incorrect characters d) Integeration of Equator Service with App Services. e) Further it can be extended to maintain Words Dictionary and to verify words as Type in Nerdle *Note, Equation Generation will be one time process and is based on requirement. So when type and rules are provided, then Equator Service will generate equations of those types and will save in DB. This equation generation API will be for Admin purpose | 1) Resilient Equator Service in NodeJS and cache Setup (Redis and its integeration with Equator service and App service) 2) Make App service resilient , in case Equator services fails, cover different scenarios 3) Unit tests for Equator Service 4) Functional Tests for Equator Service 5) Modification of Unit Tests for App Services 6) Integeration tests of App Services with Equator Services 7) Creation of environment (DEV , QA, STAGE, PROD) for equator service using cloudFormation or Terraform templates. This involves creation of resources too like DB and its configurations 8) Integeration of App Service with Equator Service with each environment (DEV,QA,STAGE,PROD) 9) Deployment of Equator Service using Jenkins pipeline to different environment 10) Creation of Sanity environments (Like QA Sanity, STAGE Sanity etc) that will trigger integeration tests after deployment of services to each environment and will generate results 11) Collection of metrics on Monitoring services like Prometheus, cloudwatch or New relic 12) Logging integeration with any services like Datadog, splunk or Amazon CloudWatch Logs 13) Alert configuration on collected metrics. 14) Integeration with PagerDuty or or any other incident reporting system 15) Load test to be performed, if we now number of requests on an average from milestone M1 or else. This will be useful for calibration of resourced involved and to get min & max thresholds. To ser Read Request Units thresholds in DB, also to decide instance sizes. *. | 1) On UI, after selecting the Equation type and Nos. of columns, App service should able to pick random equation from DB and update cache , with some temp userId (for playing user) and equation selected 2) After user enters equation in a row and submit, then App service first verify that equation is matching or not, by fetching entry from Redis. If it matches, then it will return tesponse to user, else App service will make api call to equator sericewith userId and entered equation as request param. Equator service will evaluate the equation and will return response back to App service , which will return response back to user. Below are criterias , that will be evaluated and returned by Equator service. a) Total correct characters and at the right place b) Total correct characters but not at the right place c) Total incorrect characters 3) Logs are getting collected in selected services. 6) Metrics are getting collected. 7) Alert are getting generated 8) Able to deploy successfully using Jenkins on different environment 9) Able to generate equations of different Types and different size correctly 10) Check resiliency of App services and Equator service | Metrics to analyse post deployment: 1) Average API calls 2) Average CPU utilization 3) Average Memory utilization 4) Peak load 5) CPU utilization during Peak load 6) Memory utilization during Peak load 7) DB metrics (Read/Write) 8) Cache metrics These metrics will be helpful in scaling application , alert configurations and incident reporting on production | AWS ElastiCache AWS DynamoDB